NHS Tayside

Public Records (Scotland) Act 2011

Improvement and Action Plan

Version 1.2

Version:		1.2

Document Type:	Improvement Plan

Owner/Author:		Lynda Petrie

Review Date:		April 2017

Change Control

| Date | Version | Change | Author |
| --- | --- | --- | --- |
| 24/11/2016 | 1.0 | First Draft | CRWM |
| 06/01/2017 | 1.1 | Update detail in improvement area 1.1 to reflect guidance from Keepers office around an annual update. | CRWM |
| 22/02/2017 | 1.2 | All progress status columns updated | CRWM |

PUBLIC RECORDS (SCOTLAND) ACT 2011

IMPROVEMENT AND ACTION PLAN – AN INTRODUCTION

Lynda Petrie, Corporate Records and Web Manager, has overall responsibility for achieving the implementation of this plan on behalf of Tayside NHS Board. The Board is regularly updated on progress through NHS Tayside’s Information Governance Committee and Corporate Records Compliance Group.

The Public Records (Scotland) Act 2011 requires all listed public authorities to prepare and implement a records management plan (RMP) which must set out proper arrangements for the management of its records.  The plan must clearly describe the way the authority cares for the records that it creates, in any format, whilst carrying out its business activities. The RMP must be agreed with the Keeper of the Records of Scotland (the Keeper) and regularly reviewed.

NHS Tayside submitted its RMP to the Keeper on 6 May 2016 and received an assessment report on 3 October 2016. The assessment report has been examined and is endorsed under the signature of the Keeper of the Records of Scotland as proof of compliance under section 1 of the Public Records (Scotland) Act 2011, and confirms formal agreement by the Keeper of the RMP as submitted by NHS Tayside. In agreeing this RMP, the Keeper expects NHS Tayside to fully implement the agreed RMP and meet its obligations under the Act.

The plan will be scrutinised by the Corporate Records Compliance Group, chaired by the Board Secretary, to oversee a number of improvement areas each of which are described in more detail within the Improvement Plan.

This Improvement Plan provides a clear mechanism for managing the actions committed to in the RMP submitted to the Keeper and to ensure NHS Tayside can demonstrate progress and improvements in management of its records in its next submission to the Keeper.

# Table of Contents

Element 1: Senior Officer (Green)	4

Element 2: Records Manager (Green)	4

Element 3: Policy (Green)	5

Element 4: Business Classification (Amber)	5

Element 5: Retention Schedules (Green)	7

Element 6: Destruction Arrangements (Amber)	7

Element 7: Archiving and Transfer Arrangements (Amber)	8

Element 8: Information Security (Green)	8

Element 9: Data Protection (Green)	9

Element 10: Business Continuity (Green)	9

Element 11: Audit Trail (Amber)	10

Element 12: Competency Framework for Records Management Staff (Green)	10

Element 13: Assessment and Review (Green)	11

Element 14: Shared Information (Green)	12

Third Parties (Green)	12

Improvement Area 1: Ensure RMP Submission is kept up to date	13

Elements Covered - All	13

Improvement Area 2: Appropriate Retention and Destruction	14

Elements Covered – 6, 7	14

Improvement Area 3: Improve Management of Electronic Information	15

Elements Covered – 4, 10, 11	15

Improvement Area 4: Records Management Governance	17

Elements Covered – 13	17

Improvement Area 5: Staff Engagement	18

Elements Covered – All	18

Improvement Area 6: Information Security	19

Elements Covered – 8 and 14	19

Appendix 1	21

Element 1: Senior Officer (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Any changes to named senior officer must be reported to the Keeper | As required | Corporate Records and Web Manager | As required | 1.2 | As required |

Element 2: Records Manager (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Any changes to named records managers must be reported to the Keeper | As required | Corporate Records and Web Manager | As required | 1.2 | As required |

Element 3: Policy (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Ensure updated versions of policies are shared with the Keeper during Annual Progress Update Reporting | As required | Corporate Records and Web Manager | Annually upon invitation from the Keeper | 1.1 | As required |

Element 4: Business Classification (Amber)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Development of organisational business classification scheme | November 2017 | Corporate Records and Web Manager | Share regular updates with keeper | 3.1 |  |
| 4.2 | Implementation of business classification scheme | 3-5 years | Corporate Records and Web Manager | Share regular updates with keeper | 3.2 |  |
| 4.3 | Development of organisation Information Asset Register | November 2018 | Information Governance Officer (Information Security) | Share with Keeper once developed | 3.3 |  |
| 4.4 | Ensure updated versions of NHS Tayside Departmental Records Management Plan template is shared with Keeper during Annual Progress Update Reporting | As required | Corporate Records and Web Manager | As required | 1.1 | As required |

Element 5: Retention Schedules (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 | No further action required |  |  |  |  |  |

Element 6: Destruction Arrangements (Amber)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Awareness raising campaign around appropriate retention and destruction of all record types | Ongoing | Corporate Records and Web Manager | Campaign to begin 4 November 2016 to coincide with World Paper Free Day and to continue thereafter | 5.1 |  |

Element 7: Archiving and Transfer Arrangements (Amber)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Formalise arrangements with the University of Dundee for archiving records and share agreement document with the Keeper | 2 years | Corporate Records and Web Manager | Initial meeting with Ms Brown, the University Archivist held in February 2017. Ms Brown to discuss with colleagues and draw up an initial agreement based on similar agreements in other university/health board partnerships to start discussions. | 2.1 |  |

Element 8: Information Security (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 8.1 | Ensure Keeper is updated on any progress and changes to the development of the Information Security Framework | As required | Information Governance Manager |  | 6.1 | As required |
| 8.2 | Ensure updated versions of policies are shared with the Keeper during Annual Progress Update Reporting | As required | Corporate Records and Wed Manager | As Required | 1.1 | As required |

Element 9: Data Protection (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Ensure updated versions of policies are shared with the Keeper during Annual Progress Update Reporting | As required | Corporate Records and Web Manager | As required | 1.1 | As Required |

Element 10: Business Continuity (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Update the Keeper on disaster recovery and business continuity processes for TrakCare once TrakCare is delivered | TBC reliant on TrakCare delivery timescale | Head of Service - Technical Infrastructure Manager |  | 1.1 |  |

Element 11: Audit Trail (Amber)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Address long term management of organisational shared drives | 3-5 years | Corporate Records and Web Manager |  | 3.4 |  |

Element 12: Competency Framework for Records Management Staff (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 12.1 | Ensure updated versions of documents are shared with the Keeper during Annual Progress Update Reporting | As required | Corporate Records and Web Manager & Health Records Manager | As required | 1.1 | As required |

Element 13: Assessment and Review (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 13.1 | Ensure NHS Tayside’s RMP is reviewed on a biennial basis as a minimum. | April 2018 | Corporate Records and Web Manager | Reports will be submitted to the Corporate Records Compliance Group (quarterly) Information Governance Committee (6 Monthly) Finance and Resource Committee (5 years) | N/A | As required |

Element 14: Shared Information (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 14.1 | Undertake a gap analysis of existing sharing protocols and put in place a workplan to address any identified gaps | TBC | Information Governance manager |  | As outlined |  |

Third Parties (Green)

| Ref: | Action Planned | Timescale to meet action | Responsibility for taking action | Progress | Improvement Reference | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 15.1 | Ensure procurement department builds appropriate records management provision into any future contracts to address and comply with legislation | TBC | Corporate Records and Web Manager & Health Records Manager |  | 4.2 |  |

Improvement

| Improvement Area 1: Ensure RMP Submission is kept up to date |
| --- |
| Elements Covered - All |
| Action/Improvement Work | Output | Expected Completion Date | Individuals Accountable for this task | Progress Update |
| 1.1 | Ensure Keeper of the Records of Scotland is provided with updated versions of NHS Tayside policies and documents during the Annual Progress Update Reporting Mechanism | List of documents to be kept updated with Keepers Office can be viewed at appendix 1. | Upon invitation from the Keeper | Corporate Records and Web Manager | No updates required as yet |
| 1.2 | Ensure Keeper of Records of Scotland is informed of a change of key personnel named within the RMP | List of key personnel: Lesley McLay, Chief Executive Margaret Dunning, Board Secretary Ruth Anderson, Health Records Manager Lynda Petrie, Corporate Records and Web Manager | As Required | Corporate Records and Web Manager & Corporate Records and Web Administrator | No updates required as yet |

| Improvement Area 2: Appropriate Retention and Destruction |
| --- |
| Elements Covered – 6, 7 |
| Action/Improvement Work | Output | Expected Completion Date | Individuals Accountable for this task | Progress Update |
| .1 | Liaise with Dundee University Archivist | Establish relationship and work towards an MOU for archiving arrangements for NHS Tayside records identified for permanent preservation | November 2018 | Corporate Records and Web Manager | Lynda Petrie has met with Caroline Brown from the University of Dundee Archives to kick start discussion around the creation of an MOU. |
| 2.2 | Review and update NHS Tayside’s Records Retention Schedules in line with NHS Scotland Guidelines | Keep abreast of the review of NHS Scotland guidelines and ensure NHS Tayside schedules are updated to reflect any changes made | Ongoing | Corporate Records and Web Manager | NHS Scotland Code of Records Management is currently being reviewed and updated by the Scottish Government. Once this document has been released, NHS Tayside’s own polices and guidance relying on this code will be updated to reflect changes to the code of practice. |

| Improvement Area 3: Improve Management of Electronic Information |
| --- |
| Elements Covered - 4, 10, 11 |
| Action/Improvement Work | Output | Expected Completion Date | Individuals Accountable for this task | Progress Update |

| 3.1 | Review and further develop NHS Tayside’s Business Classification Scheme (BCS) | Review and develop BCS with key colleagues and departmental records management coordinators across NHS Tayside | April 2019 | Corporate Records and Web Manager | Awaiting outcome of NHS Scotland Records Management Code of Practice review as possibility of creating a NHS Scotland wide BCS |
| --- | --- | --- | --- | --- | --- |
| 3.2 | Implement NHS Tayside BCS scheme | Implement BCS throughout organisation | April 2021 | Corporate Records and Web Manager |  |
| 3.3 | Develop NHS Tayside Information Asset Register | Feasibility study and scoping exercise undertaken. Owners and Administrators of assets identified and a standard requirement template developed to be used for data collection and assessment. | April 2019 | Information Governance Officer (Information Security) |  |
| 3.4 | Review of Long Term Shared Drive Management throughout NHS Tayside | Set up working group to review shared drive management, development, and structure throughout NHS Tayside, and move departments to use document store for records where more appropriate. This task will be closely linked to the outcome of Action 3.1 and 3.2; and input and commitment from eHealth will be required. | April 2021 | Corporate Records and Web Manager with support from eHealth and Records Management Coordinators | On hold until TrakCare is delivered to ensure eHealth have resource to input to work |

| Improvement Area 4: Records Management Governance |
| --- |
| Elements Covered - 13 |
| Action/Improvement Work | Output | Expected Completion Date | Individuals Accountable for this task | Progress Update |

| 4.1 | Ongoing review and assessment of NHS Tayside’s RMP | Report quarterly to Information Governance and Corporate Records Compliance Group on improvement plan. Report annually to Finance and Resource Committee on progress with improvement plan. | Ongoing | Corporate Records and Web Manager | Report went to F&R Committee on 16 February 2017 and to the Information Governance Committee on 31 January 2017 |
| --- | --- | --- | --- | --- | --- |
| 4.2 | Review procurement procedures to ensure records management processes are included in all procurement contracts for services | Discussions with procurement required to review current contracts and identify what changes if any need to be made |  | Corporate Records and Web Manager and Health Records Manager |  |
| 4.3 | Actively publish NHS Tayside’s RMP | Ensure RMP and assessment report is published to NHS Tayside’s website and kept up to date | January 2017 | Corporate Records and Web Manager | Actioned by Lynda Petrie in January 2017 – available at - http://www.nhstayside.scot.nhs.uk/YourRights/PublicRecordsScotlandAct/index.htm |

| Improvement Area 5: Staff Engagement |
| --- |
| Elements Covered - All |
| Action/Improvement Work | Output | Expected Completion Date | Individuals Accountable for this task | Progress Update |
| 5.1 | Awareness raising campaign around appropriate retention and destruction of all record types and general good records management principles | Remind all staff of the need to comply with schedules. First ‘drip’ of message started with NHS Tayside’s participation in World Paper Free day encouraging staff to ditch paper and to refer to schedules to assist in doing it. | Ongoing | Corporate Records and Web Manager with assistance from Communications Team/Wider Information Governance Team/Health Records Manager | Information Governance Roadshows held during September 2016 promoted retention schedules Lynda to meet with Debbie Huband to arrange a communications plan for destruction of records. |
| 5.2 | Develop a network of Records Management Coordinators throughout the organisation | An action in Audit report T35/12 was that NHS Tayside should review and refresh its network of Records Management Coordinators. Each department will be asked to identify an individual to take on this role within the department. This person should be sufficiently senior enough to have business process knowledge and the ability and drive to work through change processes in taking forward new records management practices. One to one meetings will be held with the identified people to discuss the responsibilities and expectations of this role. | Completed by Summer 2017 | Corporate Records and Web Manager | Letters issued to directors and department heads in February 2017 asking them to confirm who coordinators are. Lynda Petrie to have individual meetings with each area in Spring 2017 to discuss role and expectations fo RM Coordinators |

| Improvement Area 6: Information Security |
| --- |
| Elements Covered – 8 and 14 |
| Action/Improvement Work | Output | Expected Completion Date | Individuals Accountable for this task | Progress Update |
| 6.1 | Development of IS framework in line with DL17 | The Information Security Policy Maturity Assessment, which is based on the Information Security Policy Framework, has been used as checklist/assessment document to benchmark NHS Tayside’s current position against the requirements of the Information Security Policy Framework. NHS Tayside’s Information Governance and Security Improvement Plan will provide an action plan to address identified areas of Information Governance threats, vulnerabilities and/or weakness. A working group is to be set up to take responsibility for devising/delivering the requirements of the Information Security Policy Framework. | Ongoing | Information Governance Manager |  |
| 6.2 | Undertake a gap analysis of existing sharing protocols and put in place a workplan to address any identified gaps | The existing ISPs with local authorities have been replaced with ISPs between NHS Tayside, Local Council, NSS and the IJBs. A replacement ISP is being produced by Police Scotland for information sharing between police and NHS Boards. In addition, Scottish Government has produced a new toolkit (The Scottish Information Sharing Toolkit) which is a replacement for SASPI. At the point of review of existing agreements or when new information sharing protocols need to be put in place between parties, the new toolkit will be used. Information Governance is providing advice around production and content of ISPs where applicable. | Ongoing | Information Governance Manager |  |

# Appendix 1

| 1.1 | Health Records Strategy and Management Policy |
| --- | --- |
| 1.2 | Records Management Policy |
| 1.3 | Information Governance Policy |
| 1.4 | Policy Development, Review and Control Policy |
| 1.5 | NHS Tayside Code of Corporate Governance |
| 2.1 | Head of Health Records Job Description |
| 2.2 | Corporate Records and Web Manager Job Description |
| 3.1 | Records Creation and Registration Policy |
| 3.2 | Records Retention Schedules Policy |
| 3.6 | Health Records Operational Guidance and Service Operating Procedures |
| 4.1 | NHS Tayside Departmental RMP Template |
| 6.1 | Waste Management Policy |
| 8.1 | System Access Policy |
| 8.2 | Use of Email and Network Services Policy |
| 8.3 | Portable Computing and Removable Media Policy |
| 9.2 | Data Protection Policy |
| 14.1 | Sharing Information with the Police Policy |